## Product Backlog
User Story / Task / Requirement / Deliverable | Priority | Sprint planned | How long (hours) | Finished? | Issues with it?
Determine main requirements | M | 1 | 5 | Y
Decide project requirements | M | 1 | 10 | Y
Research Datasets | M | 1 | 16 | Y | Used dataset from Kaggle
Research AI detection in AV | M | 1 | 4 | Y
Select/Clean Dataset for Training | M | 2 | 5 | Y | Cleaned dataset included 58,000 URLs
Train/Test the model | M | 2 | 5 | Y
Build Model | M | 2 | 4 | Y
Create Flask Application | M | 3 | 8 | Y
Connect model to flask app | M | 3 | 6 | Y
Build URL Database | S | 5 | 10 | N
Build Signature-Based Detection | S | 5 or 6 | 10 | N
Connect Flask App to Web Extension Framework | M | 4 | 8 | N
Improve AI model using URL Database | C | 6 | 10 | N
Create Web Extension UI | M | 6 | 10 | N
Add Web Extension to Chrome Store | M | 7 | 5 | N
Add Web Extension to Firefox Store | S | 7 | 5 | N
Build URL Parser/Man in Middle | S | 4 | 12 | N | Need to interrupt web requests to parse URL and plug into AI model
Host flask app on Gcloud | M | 4 |  | Y
Build Pop-Up | M | 7
Add Pop-up to JS script | M | 8

## Sprint Backlog 1
Sprint 1 | 10/10/22-24/10/22 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1.Sprint Planning | 1.1 Planning with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed sprint planning | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4
2.Determine main requirements | 2.1 Identify main features | 5 | 0 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 7
| 2.2 Identify main stakeholders | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 4
| 2.3 First pass requirements | 8 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2
3.Determine project requirements | 3.1 Research web extensions | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 3.2 Research Machine Learning AV | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 3.3 Research Datasets | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 3.4 Practice Python | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
4. Review sprint | 4.1 Review progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| 4.2 Confirm with supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 33 | 29.7 | 26.4 | 23.1 | 19.8 | 16.5 | 13.2 | 9.9 | 6.6 | 3.3 | -4.4409e-15
Actual - remaining effort in Ideal hours |  | 33 | 32 | 26 | 21 | 11 | 9 | 7 | 5 | 5 | 3 | 3

## Sprint Backlog 2
Sprint 2 | 25/10/22-8/11/22 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. AI Model | 2.1 Gather Data | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2.2 Clean Data | 2 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 2.3 Test Model | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 2.4 Build Model | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
3. Review Sprint | 3.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 3.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 14 | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4 | -2.2204e-15
Actual - remaining effort in Ideal hours |  | 14 | 9.5 | 9.5 | 7 | 3 | 1 | 1 | 1 | 1 | 1 | 1

## Sprint Backlog 3
Sprint 3 | 9/11/22-23/11/22 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Flask App | 2.1 Create Base Flask App | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.2 Connect AI model to Flask | 4 | 1.5 | 1 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
| 2.3 Test the model implementation | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
3. Review Sprint | 3.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 3.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 2.2204e-15
Actual - remaining effort in Ideal hours |  | 16 | 10.5 | 7.5 | 6 | 4 | 3 | 1 | 1 | 1 | 1 | 1

## Sprint Backlog 4
Sprint 4 | 30/11/22-14/12/22 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Re-Test Model | 2.1 Research | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.2 Re-Test AI Model | 4 | 0 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
| 2.3 Improve AI Model | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 1 | 0 | 7
3. Review Sprint | 3.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1 | 1
| 3.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 2.2204e-15
Actual - remaining effort in Ideal hours |  | 16 | 12 | 8 | 6 | 6 | 5 | 3 | 0 | -1 | -2 | -2

## Sprint Backlog 5
Sprint 5 | 4/1/23-18/12/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Flask App | 2.1 Re-Implement JS Script | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.2 Update Flask Script | 1.5 | 1.5 | 1 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
| 2.3 Host Flask Script GCloud | 4 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4
3. Review Sprint | 3.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 3.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 10.5 | 9.45 | 8.4 | 7.35 | 6.3 | 5.25 | 4.2 | 3.15 | 2.1 | 1.05 | 0
Actual - remaining effort in Ideal hours |  | 10.5 | 5 | 2 | -1.5 | -1.5 | -2.5 | -4.5 | -4.5 | -4.5 | -4.5 | -4.5

## Sprint Backlog 6
Sprint 6 | 18/1/23-1/2/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. App Testing | 2.1 Test App | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 2.2 Consider Improvements | 1.5 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| 2.3 Research | 5.5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1.5 | 5.5
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 11 | 9.9 | 8.8 | 7.7 | 6.6 | 5.5 | 4.4 | 3.3 | 2.2 | 1.1 | 1.7764e-15
Actual - remaining effort in Ideal hours |  | 11 | 7 | 6 | 5.5 | 4.5 | 4.5 | 2.5 | 0.5 | 0.5 | 0.5 | -1

## Sprint Backlog 7
Sprint 7 | 8/2/23-22/2/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Pop-Up | 2.1 Build Pop-Up | 3 | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 2.2 Host Pop-Up Page GCloud | 2.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 2.5
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 5.5 | 4.95 | 4.4 | 3.85 | 3.3 | 2.75 | 2.2 | 1.65 | 1.1 | 0.55 | 8.8818e-16
Actual - remaining effort in Ideal hours |  | 5.5 | 4 | 4 | 2.5 | 2.5 | 2 | 2 | 1 | 1 | 0 | 0

## Sprint Backlog 8
Sprint 8 | 23/2/23-9/3/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Pop-Up | 2.1 Add Pop-Up to JS script | 4 | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5
| 2.2 Test Pop-Up Functionality | 4.5 | 0 | 1 | 0.5 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 4.5
| 2.3 Test Pop-Up Speed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 10.5 | 9.45 | 8.4 | 7.35 | 6.3 | 5.25 | 4.2 | 3.15 | 2.1 | 1.05 | 0
Actual - remaining effort in Ideal hours |  | 10.5 | 7.5 | 4 | 3.5 | 2.5 | 1.5 | 1.5 | -1.5 | -1.5 | -1.5 | -1.5

## Sprint Backlog 9
Sprint 9 | 13/3/23-26/3/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Research and Training | 2.1 Peer Feedback | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| 2.2 Research | 7 | 0 | 2 | 0 | 0.5 | 1 | 1 | 0 | 2 | 0.5 | 0 | 7
| 3.3 Train New Model | 6.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 16.5 | 14.85 | 13.2 | 11.55 | 9.9 | 8.25 | 6.6 | 4.95 | 3.3 | 1.65 | -2.2204e-15
Actual - remaining effort in Ideal hours |  | 16.5 | 14.5 | 11.5 | 10.5 | 10 | 9 | 7.5 | 7.5 | 5.5 | 5 | 5

## Sprint Backlog 10
Sprint 9 | 27/3/23-10/4/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. New AI Model | 2.1 Test New Model | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.2 Create New Flask App | 4 | 1.5 | 1 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
| 2.3 Create New JS Script | 6.5 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 14.5 | 13.05 | 11.6 | 10.15 | 8.7 | 7.25 | 5.8 | 4.35 | 2.9 | 1.45 | 2.2204e-15
Actual - remaining effort in Ideal hours |  | 14.5 | 9 | 6 | 4.5 | 2.5 | 1.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5

## Sprint Backlog 11
Sprint 11 | 17/4/23-1/5/23 |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 1.2. Detailed planning with Team | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2. Flask App | 2.1 Upload Add-On Firefox | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| 2.2 Test Add-On from download page | 4 | 1.5 | 1 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
|  | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 4
3. Review Sprint | 4.1 Review Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| 4.2 Confirm with Supervisor | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  | 14 | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4 | -2.2204e-15
Actual - remaining effort in Ideal hours |  | 14 | 7.5 | 4.5 | 3 | 1 | 0 | -2 | -2 | -2 | -2 | -2